## Sheet1
ID | Activity | Duration | Dependency | Start Date | Finish Date
1 | Project Planning and Requirements Analysis | 1 Day | None | 2026-07-27 | 2026-07-27
2 | Select Prototype Approach | 1 Day | 1FS | 2026-07-28 | 2026-07-28
3 | Draft Low-Fidelity Prototype Screen 1 | 1 Day | 2FS | 2026-07-29 | 2026-07-29
4 | Draft Context Diagram | 1 Day | 1FS | 2026-07-28 | 2026-07-28
5 | Create Level-0 DFD | 1 Day | 4FS | 2026-07-29 | 2026-07-29
6 | Identify System Actors and Main Use Cases | 1 Day | 1FS | 2026-07-28 | 2026-07-28
7 | Draft Initial Use Case Diagram | 1 Day | 6FS | 2026-07-29 | 2026-07-29
8 | Draft Use Case 1 Documentation | 1 Day | 6FS | 2026-07-29 | 2026-07-29
9 | Identify Two Major Business Processes | 1 Day | 1FS | 2026-07-28 | 2026-07-28
10 | Draft Activity Diagram 1 | 1Day | 6FS,9FS | 2026-07-29 | 2026-07-29